The Compliance Certification

TSTC Harlingen

SACS Class of 2005 Track A

Timeline of all Activities for Compliance Certification (Due March 15, 2004):

| DATE | ACTIVITY |
| --- | --- |
| Fall 2003 | Preliminary SACS Leadership Team Selected (SLT); but later revised into a smaller group IER staff works with IT staff to discuss needs of SACS electronic submission; process for submitting narratives/documentation; develops and programs SACS Reaffirmation secure database web site for collection of information |
| Dec. 2003- Jan. 2004 | IER office conducts mandatory training sessions for all TSTC Harlingen employees re: Principles of Accreditation; introduces campus to concept of a QEP and told to consider focus options |
| late January 2004 | TSTC Harlingen representatives attend SACS Orientation session in Atlanta (President, SACS Accreditation Liaison, VP Instruction, VP Student Services) |
| Jan. – Feb. 2004 | Select a “theme” for college’s SACS reaffirmation process; create a SACS handbook, plan college-wide “SACS Kick off” |
| Feb. 2004 | Assign each Principle to a member of SLT who may select an “editor” to help enter data/info onto SACS database. Each SLT member assigned must determine scope of narrative, all documents needed for inclusion, create any missing documents or begin processes not yet begun, write entire narrative |
|  | Each SLT member brings in others from college as needed to provide information, documentation, or input into narrative response All Principles briefly reviewed by entire SLT and complexity of response determined; timeline set for submission of each fully completed Principle between March and December 2004. More involved, complex narratives, or those requiring processes still to be implemented, given later due dates |
| Feb. 2004 | IER Staff completes report revisiting the history of TSTC Harlingen’s past performance with SACS reaffirmation. “TSTC Harlingen & SACS: A Historical Perspective,” was created and reviewed by the SLT to determine the extent to which each area of non-compliance in ’95 had been given satisfactory attention, plans since implemented, and assessed |
| Feb. 2004 | SLT determines standard format for each narrative to follow: State compliance with requirement State person(s) (administrator) responsible for all parts of the requirement Divide each principle into all “sections” of requirement to be addressed—use as section headings Describe processes thoroughly, embed data and information via links within the narrative to the documentation Put documentation into tables, databases, drop-down lists, etc. for ease of access & thoroughness |
| March 2004 | Campus wide “SACS Kickoff” Celebration to introduce college to reaffirmation processes that will be occurring |
| March 2004 – December 2004 | SLT meets monthly to review narratives due, accept or debate submissions, determine any omissions, determine thoroughness of response, adequacy of documentation, etc. |
| December | Attend SACS Annual meeting; hear more about pilots and first class after pilots; hear praise about Citadel’s approach to Compliance Certification |
| February 2004 | Receive completed audits and other financial docs. and complete all narratives re: finances/audits |
| Jan.- Feb. 2004 | Edit and re-write all narratives as needed to put into better format for reader, less reading, less tedious, more databases, pictures, condense writing (used Citadel model) English faculty with little knowledge of Principles serve as final reader/editor for final narratives Electronic numbering changes to database Cross-referencing & access to all electronic docs tested Work on web-site completing “reference library” section of report, final changes fill final weeks/days up to Mar. 15 deadline |
| March 2004 | Create instructions for accessing electronic narratives Burn CDs Make copies of written narratives (no documentation) and bind into booklet for off-site team Create packages of information, booklets, catalogs, etc. to send to SACS and off-site team Mail completed packages to off-site team |
| May 2004 | Off-site team reviews Compliance Certification |
| June 2004 | Telephone conference call with SACS Staff re: Off-site review results; One “does not meet compliance” and five “could not determine compliance” Note: All areas of follow-up were the result of broken links the reviewers could not access (employee database, policies) and area of non-compliance required change to one sentence of college’s graduation policy |
| Summer 2004 | Worked to correct and gather hard copies of documents that could not be accessed and led to “could not determine” compliance findings; Completed content for Focused Report |
| August 26,2004 | Submitted QEP and Focused Report ( all hard copy—no electronic submission of Focused Report) |
| Oct. 11-13, 2004 | On-Site SACS Committee Visit Findings: NO RECOMMENDATIONS |

Documenting Your Processes

The following processes were fully created, significantly updated, or converted to electronic format to meet SACS requirements:

Created:

Bios for all administrators on Employee Profiles (Database)

Websites for as many student activities/clubs as possible

Assessment Plans for ALL Instructional and Student Services Departments (Database)

On-line Fact Book, Query Tool (Database)

Closing the Loop Examples (Database)

“Table”/ Database with photos of each program’s labs, library labs, open labs, etc.

Table of outside/program accreditations

Employee (Faculty) Profiles by Name, degrees earned, certifications & licenses, courses 	taught for previous three semesters, work history, awards and honors (database)

Updated:

All position descriptions (Database)

All applicable policies & procedures (Database)

Club and Program/dept. websites

Converted to Electronic Format:

All IER Surveys and studies

Strategic Plans (two cycles)

Master Plan

Closing the Gaps Plan

IT Strategic Plan

Operational Plan

Easy viewable access to Unit Action Plans for 2 Cycles, all Depts. (Database)

Internal Review Processes/ Reports

All Assessment Plans and their Reports of Results (Databases)

All MOUs and Articulation Agreements

All Financial Statements and Audits

All Recruitment materials

All Handbooks not yet converted to electronic format

Evaluation forms

Unit budgeting procedures (linked to planning)

All Instructional Department Reports

Used Outside Links to:

Vernon’s Texas Education Code

Roberts Rules of Order

Board By-laws

THECB: 	General Academic Course Manual

WECM

Annual Data Profile

Classroom Utilization Reports

Facilities Inventory

Space Model

MP1

MP2&3

MP4

Perkins Measures & Outcomes

Annual Licensure Report

State of Texas Purchase Voucher Guide

General Appropriations Act

Prompt Payment Act

Facilities Inventory Data

State Auditor’s Office

State Office of Risk Management

State Fire Marshall

OSHA

Texas Common Course Numbering System Matrix

LBB

VCT Manuals

Tech Prep Articulation Agreements

ALA for ACLR Standards

American Dental Association Accreditation Standards

CAAHEP Accreditation Standards

ASE/NATEF Certification Standards

TexShare

CAS (Council for the Advancement of Standards for Student Affairs Programs)

Legislation/House Bills

State statutes—	Open meeting requirements

Financial statement requirements

Political activities by public entities

Filing of complaints

Officer and employee ethics

Prohibited acts of agencies and individuals

Impeachment and Removal

Appointment of Board

FERPA

Higher Education Amendments of 1998