- Green text:  represents activities similar to what the college is already engaged in on an ongoing basis. Some of these activities are performed as a matter of the college's standard operating procedures.

- Blue text:  represents activities similar to those in which the college is already engaged. These activities will have to be further developed and/or expanded in order to meet the assessment and evaluation needs presented by the QEP.

- Red text:  represents new activities to be developed and/or implemented as a direct result of the QEP.

Sample from Evaluation of QEP – Integration Process, Student Learning, and Implementation

Texas State Technical College West Texas

| I. Assessment of Process of Integration of Soft Skills Across the Curriculum |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objective/Activity | Evaluation Method | Rationale for Evaluation Method | Timeframe | Responsible Parties |
| Faculty Development for Professional Development Course | Surveys of training process (green) | Surveys should indicate needed revisions/improvements to the faculty development process. | End of summer term/fall 2004 On-going as faculty change | PD Course Faculty Development Committee, QEP Team |
| Professional Development Course | a. Midterm status check with faculty 1 (green) b. PD Course Advisory Committee Review of Pre- and Post-Survey of Student Self Assessment 2 (blue) c. PD Course Advisory Committee Review of attendance, retention to next term (red) | As the foundation course for soft skills, the evaluation of the process and the results will set the stage for further evaluation activities and the assessment of student learning. | Mid-term status check End of each term | PD Course Coordinator, PD Course Faculty, PD Faculty Development for Prof Dev Course Subcommittee, PD Course Advisory Committee, QEP Team |
| Professional Development Training | Evaluation Surveys for faculty and staff workshops (green) | Professional development is key to successful integration of soft skills. Determining the value of each training will allow the team to improve future training, expand on past trainings | Winter/spring each year beginning 2005 | SSI Faculty Development Team |